Autonomous Lead Generation

System Specification

Burkhart Brothers Construction  |  Orange County, California

March 2026  |  Confidential  |  v1.0

| 90 Total Hours | 10+80 Alpha + Build | 16 Hours Completed | Weekly Report Delivery |
| --- | --- | --- | --- |

|  | Engagement Structure |
| --- | --- |

This project is structured in two phases: a 10-hour Alpha feasibility phase to validate the approach, followed by an 80-hour implementation phase to build the complete autonomous system.

| Phase | Scope | Role | Hours |
| --- | --- | --- | --- |
| Alpha | Feasibility & validation | CTO | 10 |
| Build | Full system implementation | CTO | 10 |
| Build | Full system implementation | Development | 70 |

16 hours of foundational work have already been completed—9 city permit scrapers are live and operational, along with the client-fit scoring engine and OC Assessor API integration. This prior investment accelerates the remaining build.

|  | Alpha Phase — Feasibility & Validation (10 hrs CTO) |
| --- | --- |

Before committing to the full build, we validate that every data source is accessible, every scraping approach is viable, and the architecture will support autonomous weekly operation. This phase produces a go/no-go recommendation with a validated technical approach.

| Activity | Description | Hours |
| --- | --- | --- |
| Scraper Connectivity Audit | Test all 9 live scrapers end-to-end. Verify login flows (Tyler SSO, eTRAKiT, Newport Beach 2FA), confirm data shape hasn’t changed, identify any portal updates that need adaptation | 2 |
| DRB Source Validation | Access Laguna Beach Granicus, confirm agenda format, test PDF staff report downloads, verify plan set links resolve. Test Legistar API for Newport Beach. Confirm data is extractable | 2 |
| Just-Sold Feasibility | Test Zillow/Redfin/Realtor.com scraping in target HOA areas. Validate buyer agent data is accessible (not hidden behind auth). Assess anti-bot measures and rate limits | 2 |
| Contact Enrichment Test | Validate Spokeo automation (login, search by name, extract results). Test Apollo.io API for architect lookups. Confirm enrichment data quality meets expectations | 1 |
| Architecture & Pipeline Design | Design orchestrator architecture, data schema, dedup strategy, error recovery approach. Define the unified lead record format that all sources feed into | 2 |
| Alpha Report & Recommendation | Deliver written findings: what works, what needs workarounds, any blockers identified. Go/no-go recommendation with adjusted estimates if scope changed | 1 |

| Alpha | Feasibility & Validation | 10 hrs CTO |
| --- | --- | --- |

Alpha Deliverable: Written feasibility report with go/no-go recommendation, validated data source access, confirmed architecture approach, and refined estimates for the implementation phase. If blockers are discovered, we identify workarounds or adjust scope before committing development resources.

|  | System Architecture |
| --- | --- |

The production system is organized into four tiers that execute sequentially on each automated run:

| Tier | Function | Components |
| --- | --- | --- |
| 1. Collection | Scrape raw data from all sources | 9 city permit scrapers, DRB scraper, just-sold monitor, CDP scraper |
| 2. Processing | Filter, score, deduplicate | Client-fit filter, 10-point scoring engine, address-based deduplication |
| 3. Enrichment | Append owner/architect contact info | OC Assessor API, Spokeo by-name lookup, Apollo.io architect search |
| 4. Delivery | Generate and send reports | CSV/JSON export, branded DOCX report, email via MS 365 |

Runtime Environment

- Platform — Windows 11 desktop session (required for Playwright browser automation)

- Runtime — Node.js 18+ with Playwright for all browser-based scraping

- Scheduling — Windows Task Scheduler triggers PowerShell orchestrator under user account

- AI Layer — AI-powered supervisor monitors scraper health, diagnoses failures, triggers re-runs

- Credentials — All credentials stored in .env file at project root, never committed to git

|  | Implementation Phase — 80 Hours (10 CTO + 70 Dev) |
| --- | --- |

After Alpha validation, the full system is built in six development phases with CTO oversight on architecture, integration, and quality.

CTO Responsibilities (10 hours)

| Activity | Description | Hours |
| --- | --- | --- |
| Architecture & Technical Design | System architecture decisions, orchestrator design, data schema, API integration patterns, error recovery strategy | 3 |
| Integration & Oversight | Code review of scraper implementations, integration testing across all data sources, performance optimization | 3 |
| Scoring Calibration | Work with Kurtis to validate lead scoring against his manual assessments, tune weights and thresholds for each signal | 2 |
| Deployment & Handoff | Production deployment, scheduled task configuration, monitoring setup, operational documentation and runbook | 2 |

| CTO | Architecture, Oversight & Deployment | 10 hrs |
| --- | --- | --- |

Development Phase 1 — Orchestrator & Supervisor (12 hrs)

Central PowerShell supervisor and Node.js orchestrator that coordinates all scrapers, manages scheduling, and handles error recovery.

| Component | Description | Hours |
| --- | --- | --- |
| PowerShell Supervisor | Main entry point. Pre-flight checks (Node, Playwright, .env), launches orchestrator, captures exit codes, writes structured logs, sends health alerts on failure | 4 |
| Node.js Orchestrator | Runs all scrapers in configured order, manages parallel execution for independent scrapers, collects results into unified lead schema, handles timeouts and retries | 4 |
| Aggregator + Dedup | Merge results from all sources, deduplicate by normalized address, flag multi-source leads for bonus scoring points | 2 |
| Windows Scheduled Task | Task Scheduler configuration for tiered cadence: permits weekly, just-solds daily, DRB after meetings. Runs under user desktop session | 2 |

| P1 | Orchestrator & Supervisor | 12 hrs Dev |
| --- | --- | --- |

Development Phase 2 — DRB Intelligence (16 hrs)

Automated Design Review Board scraping—replaces Kurtis’s primary manual workflow of reading DRB agendas and extracting owner/architect names from linked plan sets.

| Component | Description | Hours |
| --- | --- | --- |
| Granicus Agenda Parser | Parse meeting listings for Laguna Beach DRB, Costa Mesa, SJC, Irvine, Dana Point. Extract agenda items with project descriptions and staff recommendations | 5 |
| Legistar Integration | Parse Legistar API for Newport Beach Planning Commission, City of Orange DRC. Extract matter details, staff reports, and attachments | 4 |
| PDF Staff Report Parser | Download and parse staff report PDFs for recommendation status (approve/deny/continue), project scope, and square footage | 4 |
| Plan Set Title Block Extraction | Extract owner name and architect from plan set PDF title blocks using text extraction | 3 |

| P2 | DRB Intelligence Scraper | 16 hrs Dev |
| --- | --- | --- |

Development Phase 3 — Just-Sold Monitor (14 hrs)

Monitor real estate platforms for recent luxury sales in the 18 target HOA communities. Extract buyer agent contact info—the warm introduction path to new homeowners planning renovations or rebuilds.

| Component | Description | Hours |
| --- | --- | --- |
| Zillow Scraper | Search by HOA community/zip, filter >$3M SFR, extract sale price, buyer agent name, brokerage, sale date, address | 4 |
| Redfin Scraper | Search recently sold in target areas, last 90 days, SFR only. Extract buyer agent, MLS data, flag homes built pre-2000 as rebuild candidates | 4 |
| Realtor.com Scraper | Supplementary MLS-direct source. Focus on older homes in target HOAs | 3 |
| Anti-Detection & Rate Limiting | Request throttling, session management, user-agent handling to maintain reliable access to real estate platforms | 3 |

| P3 | Just-Sold Monitor | 14 hrs Dev |
| --- | --- | --- |

Development Phase 4 — Contact Enrichment (10 hrs)

Automated skip tracing and contact enrichment. Transforms leads into actionable contacts with owner phone/email and architect details.

| Component | Description | Hours |
| --- | --- | --- |
| Spokeo Automation | Browser-based Spokeo search by owner NAME (never address). Login with stored credentials, extract phone and email. Queue-based processing so enrichment doesn’t block reports | 5 |
| Apollo.io Integration | API-based architect contact lookup by name + firm. Return direct email and LinkedIn profile for architect outreach | 3 |
| OC Assessor Batch Extension | Extend existing OC Assessor integration for batch processing. Auto-flag properties >$5M as ultra-high-net-worth qualifier | 2 |

| P4 | Contact Enrichment Pipeline | 10 hrs Dev |
| --- | --- | --- |

Development Phase 5 — CDP & Financial Signals (8 hrs)

Coastal Development Permits and OC Clerk-Recorder financial signals add high-conviction lead indicators.

| Component | Description | Hours |
| --- | --- | --- |
| CDP Scraper — 5 Cities | Scrape CDP filings from Huntington Beach, Newport Beach, Laguna Beach, Dana Point, San Clemente planning portals and CA Coastal Commission | 5 |
| OC Clerk-Recorder Monitor | Search for construction deeds of trust and LLC/trust property transfers in target areas. Integrate as scoring signals | 3 |

| P5 | CDP & Financial Signals | 8 hrs Dev |
| --- | --- | --- |

Development Phase 6 — Report & Email Delivery (10 hrs)

Automated weekly report generation with email delivery to the client via Microsoft 365 integration.

| Component | Description | Hours |
| --- | --- | --- |
| Weekly Report Generator | Generate tiered lead report: Tier 1 (Hot), Tier 2 (Warm), Tier 3 (Watch). CSV for CRM import, JSON for data consumers | 3 |
| Branded DOCX Builder | Extend existing Technijian-branded DOCX template for weekly reports. New leads highlighted, source attribution, scoring breakdown | 3 |
| MS 365 Email Integration | Configure MS 365 MCP server with OAuth. Compose and send weekly email to Kurtis with DOCX/CSV attachments | 2 |
| Delta Detection & Archive | Track previously sent leads. Highlight only NEW leads per report. Archive weekly snapshots to data/reports/YYYY-MM-DD/ | 2 |

| P6 | Report & Email Delivery | 10 hrs Dev |
| --- | --- | --- |

|  | Labor Summary |
| --- | --- |

| Phase | Scope | CTO | Dev | Total |
| --- | --- | --- | --- | --- |
| Alpha | Feasibility & Validation | 10 | — | 10 |
| P1 | Orchestrator & Supervisor | — | 12 | 12 |
| P2 | DRB Intelligence Scraper | — | 16 | 16 |
| P3 | Just-Sold Monitor | — | 14 | 14 |
| P4 | Contact Enrichment Pipeline | — | 10 | 10 |
| P5 | CDP & Financial Signals | — | 8 | 8 |
| P6 | Report & Email Delivery | — | 10 | 10 |
| CTO | Architecture, Oversight, Deploy | 10 | — | 10 |

| 90 Total Hours | 20 CTO Hours | 70 Development Hours | 16 Already Completed |
| --- | --- | --- | --- |

|  | Implementation Schedule |
| --- | --- |

Alpha runs first as a standalone validation. After go-ahead, development phases 2 and 3 can run in parallel. CTO hours are distributed across all weeks.

| Week | Phase | Milestone | Deliverable |
| --- | --- | --- | --- |
| 1 | Alpha | Feasibility validated | Written go/no-go report, architecture design |
| 2–3 | P1 | Orchestrator operational | PowerShell supervisor, scheduled tasks, logging |
| 3–4 | P2 | DRB scraper live | Granicus/Legistar parser, PDF title block extraction |
| 3–4 | P3 | Just-sold monitor live | Zillow/Redfin/Realtor scrapers, buyer agent data |
| 5 | P4 | Contact enrichment integrated | Spokeo + Apollo.io automation |
| 5–6 | P5 | CDP + financial signals live | 5-city CDP scraper, Clerk-Recorder monitor |
| 6 | P6 | Report + email delivery | Weekly DOCX/CSV, MS 365 email to client |
| 6–7 | CTO | Deployment & calibration | Scoring calibration, production handoff |

|  | Automated Run Cadence |
| --- | --- |

| Source | Cadence | Schedule | Rationale |
| --- | --- | --- | --- |
| City Permits (9) | Weekly | Sunday 6:00 AM | Permits update slowly, weekly is sufficient |
| DRB Agendas | After each meeting | Daily check, scrape on new | Laguna Beach 2x/month, others vary |
| Just-Sold Listings | Daily | Mon–Fri 7:00 AM | Fresh sales go stale fast |
| CDP Filings | Weekly | Sunday 6:30 AM | Coastal permits filed infrequently |
| Contact Enrichment | On new leads | After each scrape cycle | Only enrich newly discovered leads |
| Report + Email | Weekly | Sunday 10:00 AM | Consolidated digest after all scrapes |

|  | Existing Assets (16 hrs completed) |
| --- | --- |

| Asset | Status | Notes |
| --- | --- | --- |
| Newport Beach permit scraper | Live | Tyler EnerGov (2FA via Gmail) |
| Laguna Beach permit scraper | Live | Tyler EnerGov with SSO login |
| Costa Mesa permit scraper | Live | Tyler EnerGov (no auth) |
| Laguna Niguel permit scraper | Live | Tyler EnerGov (no auth) |
| San Juan Capistrano scraper | Live | CentralSquare eTRAKiT |
| Dana Point permit scraper | Live | CentralSquare eTRAKiT (free account) |
| San Clemente permit scraper | Live | CentralSquare eTRAKiT |
| Irvine permit scraper | Live | Custom ASP.NET portal |
| Client-fit filter + scoring | Live | Shared module (agents/shared/client-fit.js) |
| OC Assessor API integration | Live | Property value lookup by APN |
| Branded DOCX generation | Live | Technijian-branded reports |

|  | Future Phase — Lead Management Web Application |
| --- | --- |

Once the autonomous lead pipeline is proven and delivering consistent weekly results, the natural evolution is a full-featured web application that puts Burkhart Brothers in complete control of their lead intelligence operation.

This phase is offered as a separate engagement after the core system is operational and validated. It transforms the current automated pipeline into a self-service platform that Burkhart Brothers owns and manages independently, with Technijian providing ongoing maintenance and support.

What the Web Application Adds

| Capability | Current System | Web Application |
| --- | --- | --- |
| Lead Visibility | Weekly CSV/DOCX email report | Real-time dashboard with live lead feed, filtering, and search |
| Lead Management | Read-only reports | Assign leads to team members, track outreach status, log notes and call outcomes |
| Scoring Control | Fixed scoring weights | Adjustable scoring sliders—Kurtis tunes weights without developer involvement |
| Source Management | Developer-configured scrapers | Enable/disable sources, add new HOA targets, adjust search filters via UI |
| Contact Tracking | Contact info in spreadsheet | Built-in CRM: owner profiles, communication history, follow-up reminders |
| Pipeline View | Static tier grouping | Kanban board: New → Contacted → Meeting → Proposal → Won/Lost |
| Reporting | Weekly snapshot | On-demand reports, trend analytics, conversion tracking, ROI by source |
| Multi-User | Single recipient | Team access with role-based permissions (admin, sales, read-only) |
| Notifications | Weekly email only | Real-time alerts: Tier 1 lead detected, score change, new source match |
| Mobile Access | Desktop only | Responsive web app—review leads from phone on job sites |

Proposed Technology Stack

| Layer | Technology | Why |
| --- | --- | --- |
| Frontend | React 18 + Tailwind CSS | Modern, responsive UI with real-time updates |
| Backend | .NET 8 Web API | Enterprise-grade API with Dapper + stored procedures |
| Database | SQL Server | Relational data for leads, contacts, pipeline stages, audit trail |
| Authentication | Microsoft Entra ID (Azure AD) | SSO with existing Microsoft 365 accounts |
| Hosting | Azure App Service | Scalable cloud hosting with CI/CD pipeline |
| Lead Engine | Existing Node.js scrapers | Current pipeline feeds into the web app database |

Key Features

- Live Map View — Interactive lead map showing all active projects across 11 OC cities with color-coded pins by tier

- Multi-Source Timeline — Side-by-side comparison of leads from different sources with unified timeline of all signals for each property

- Outreach Automation — Automated outreach tracking: log calls, emails, meetings. Set follow-up reminders with push notifications

- Analytics Dashboard — Monthly and quarterly analytics: leads by source, conversion rates, time-to-contact, pipeline velocity

- Self-Service Config — Configure which HOAs, cities, scoring weights, and notification thresholds to use—no developer needed

- Compliance & Audit — Full audit trail of every lead: when discovered, from which source, score changes, outreach history

Engagement Model

| Item | Description |
| --- | --- |
| Web App Build | Separate SOW scoped after core system is proven (estimated 200–300 hours) |
| Ownership | Burkhart Brothers owns the application and all data—hosted in their Azure tenant |
| Maintenance | Technijian provides ongoing maintenance: scraper updates when portals change, feature enhancements, security patches |
| Support SLA | Monthly retainer for support, monitoring, and up to 8 hours/month of enhancements |
| Training | Onboarding session for Kurtis and team—admin panel walkthrough, scoring configuration, pipeline management |

The web application is a natural Phase 2 once the autonomous pipeline proves its value. Start with the 90-hour core build, validate lead quality and ROI, then invest in the full platform when ready. No commitment required until you’ve seen results.

Technijian ¦ Autonomous Lead Generation ¦ rjain@technijian.com ¦ 949.379.8500