## TimeEntries
Contract | Date Requested | Title | Requestor | Category | Start | End | Normal Qty | Normal Rate | AH Qty | AH Rate | Total | Resource | POD | RoleType | WorkType | Note
Under Contract | 7/20/2023 | FM documentation | Vintage Design | Desktop Work | 7/20/2023 12:30:00 PM | 7/20/2023 1:30:00 PM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | FAM Audit Documentation from Mark Reviewing
Under Contract | 7/21/2023 | VDI095-MB ,VDI099-MB,VDI114,VDI115,VDI118,VDI118-Latest screenconnect services through backend | Vintage Design | My Remote | 7/21/2023 7:15:00 PM | 7/21/2023 8:08:00 PM | 0.75 | 0 | 0.13 | 0 | 0 | R. Uniyal | CHD-TS1 | Support | Remote | During the routeine work checked clients machine which require latest screen connect services so installed latest screen connect services without taking a remote of users.Reinstalled a mY remote on backend.Computers were below: VDI095-MB ,VDI099-MB,VDI114,VDI115,VDI118,VDI118-Latest screen connect services through backend.
Under Contract | 7/21/2023 | Re: Laptop Issues vintage | Vintage Design | User Generated | 7/21/2023 7:30:00 PM | 7/21/2023 8:21:00 PM | 0.5 | 0 | 0.35 | 0 | 0 | S. Chamoli | CHD-TS1 | Support | Remote | Got mail from Douglas regarding, Issue on nick computer with inbound and outbound mail troubleshoot on it test mail flow and sync all folder ,Aslo repair corrupt files and update window patches to fix the menu not clickable issue, Confirmed with Nick and close the ticket.
Under Contract | 7/21/2023 | RE: Printer Help | Vintage Design | User Generated | 7/21/2023 11:00:00 PM | 7/21/2023 11:35:00 PM | 0 | 0 | 0.58 | 0 | 0 | S. Kumar | CHD-TS1 | Support | Remote | as per the email connected to the user's machine and installed the printer as advised by the user and checked test printing along with the user. Now it is working fine. Hence Closing this ticket
Under Contract | 7/21/2023 | Please install and setup Veeam Agent on all VTD VMs | Vintage Design | Project Work | 7/21/2023 12:00:00 PM | 7/21/2023 1:00:00 PM | 1 | 0 | 0 | 0 | 0 | G. Kumar | CHD-TS1 | Support | Remote | As per instructions from Hamid accessed all the VMs again and changed the backup scheduled time and started the backups and give the list with the issue of Vm and size of the Vma nd stopped and disabled the backup jobs for all the HV.
Under Contract | 7/22/2023 | Worked on VTD backups | Vintage Design | Project Work | 7/22/2023 1:00:00 PM | 7/22/2023 1:40:00 PM | 0.67 | 0 | 0 | 0 | 0 | G. Kumar | CHD-TS1 | Support | Remote | Worked on VTD backups and added the missing machines as well. some of backups are in progress and handover to the next shift for the monitor.
Under Contract | 7/22/2023 | VDI178,VDI147,VDI143-Latest screenconnect services through backend | Vintage Design | My RMM | 7/22/2023 6:28:00 PM | 7/22/2023 7:04:00 PM | 0.6 | 0 | 0 | 0 | 0 | R. Uniyal | CHD-TS1 | Support | Remote | During the routeine work checked clients machine which require latest screen connect services so installed latest screen connect services without taking a remote of users.Reinstalled a mY remote on backend.Computers were below: VDI095-MB ,VDI178,vdi147,vdi143-Latest screen connect services through backend.Also verified after updated the services.
Under Contract | 7/23/2023 | ScreenConnect Ver. 23.5.7.8593 updated on the following machines - VDI189, VDI190 | Vintage Design | My Remote | 7/23/2023 12:00:00 AM | 7/23/2023 12:20:00 AM | 0 | 0 | 0.33 | 0 | 0 | S. Kumar | CHD-TS1 | Support | Remote | Checked on the portal, and found below the computers run with the old version. Need to update with the latest version for my remote. Download and updated the latest version(23.5.7.8593) on the Computers. Now It shows updated. Hence Closing this ticket VDI189,VDI190
Under Contract | 7/24/2023 | VDI181,VDI167,VDI197-My Remote tool services updated through backend | Vintage Design | My Remote | 7/24/2023 6:32:00 PM | 7/24/2023 7:05:00 PM | 0.55 | 0 | 0 | 0 | 0 | R. Uniyal | CHD-TS1 | Support | Remote | During the routeine work checked clients machine which require latest screen connect services so installed latest screen connect services without taking a remote of users.Reinstalled a my remote on backend.Computers were below: VDI181,VDI167,VDI197-Latest screen connect services through backend.Also verified after updated the services.
Under Contract | 7/24/2023 | remote apps not accessible | Vintage Design | Server Work | 7/24/2023 7:00:00 AM | 7/24/2023 8:00:00 AM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Assisted with server work and remote apps. They were not accessible, time out of sync on dc1 and ra01 was locked and needed a reboot.
Under Contract | 7/24/2023 | RE: URGENT! Remote session not working | Vintage Design | User Generated | 7/24/2023 8:24:00 PM | 7/24/2023 8:49:00 PM | 0 | 0 | 0.42 | 0 | 0 | S. Chamoli | CHD-TS1 | Support | Remote | Got multiple mail from VTD user regrading not able to connect to RDP check all the RDP services, also server IRRA01 frozen on black screen rests the server from Hypervisor, Manually set the time on server ,Took assist from shift lead shiveni
Under Contract | 7/24/2023 | RE: URGENT! Remote session not working | Vintage Design | User Generated | 7/24/2023 6:45:00 PM | 7/24/2023 7:15:00 PM | 0.5 | 0 | 0 | 0 | 0 | S. Koshal | CHD-TS1 | Support | Remote | Multiple users had an issue with connecting to Remote session, checked the remote server IRRA01 was frozen so rebooted that from HV04 & then checked DC01 & found time was wrong so reset the time, synced the servers & then tested Remote session it was working fine. Issue was resolved confirmed with users
Under Contract | 7/24/2023 | myremote setup | Vintage Design | Desktop Work | 7/24/2023 10:00:00 AM | 7/24/2023 10:15:00 AM | 0.25 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Setup Natalie Rooskandcar
Under Contract | 7/24/2023 | Updating SSL Cert | Vintage Design | Domain SSL | 7/24/2023 1:29:00 PM | 7/24/2023 2:47:00 PM | 1.3 | 0 | 0 | 0 | 0 | J. Chou | IRV-TS1 | Support | Remote | Checking the SSL renewals. Looks like it is on auto-renew. Getting the ssl for nextgen. Updating ssl for IIS. Not sure how to update the filemaker with the new cert. Need to find the pem key for the cert to work. Generate a new csr. Rekey the cert. Finally update the ssl cert for filemaker. Document SSL
Under Contract | 7/24/2023 | S90 equipment pickup | Vintage Design | Desktop Work | 7/24/2023 2:30:00 PM | 7/24/2023 3:30:00 PM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Went onsite and picked up QNAP and unitends.
Under Contract | 7/24/2023 | Screenconnect version updated on machines VDI184 | Vintage Design | My Remote | 7/24/2023 4:25:00 AM | 7/24/2023 4:40:00 AM | 0 | 0 | 0.25 | 0 | 0 | S. Sharma | CHD-TS1 | Support | Remote | Review the my remote portal, and found the machine VDI184 running with old version of screenconnect. So reinstalled the latest version 23.5.7.8593. from my remote portal. After that refresh the machine from the portal. It was updated to latest version. Hence closing this ticket.
Under Contract | 7/25/2023 | Software cleanup | Vintage Design | Desktop Work | 7/25/2023 7:30:00 AM | 7/25/2023 8:30:00 AM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Going through all servers at Vintage, removing software, bitdefender and other s90 software
Under Contract | 7/25/2023 | New Hire documentation with Doug | Vintage Design | Desktop Work | 7/25/2023 8:30:00 AM | 7/25/2023 9:30:00 AM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | New hire documentation with Doug
Under Contract | 7/25/2023 | Nextgen services down | Vintage Design | Desktop Work | 7/25/2023 9:30:00 AM | 7/25/2023 10:00:00 AM | 0.5 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Addressing issues reported for ngweb reboted irnx05 and troubleshot.
Under Contract | 7/25/2023 | Vintage Design - Remote | Vintage Design | User Generated | 7/25/2023 11:20:00 PM | 7/25/2023 11:59:00 PM | 0 | 0 | 0.65 | 0 | 0 | A. Bhardwaj | CHD-TS1 | Support | Remote | Email was received from client. Requested user to create a new remote session and then login to user machine. troubleshoot the issue with client VPN issue and RDP issue.
Under Contract | 7/25/2023 | Screenconnect version 23.5.7.8593 updated on machines VDI164,VDI191,VDI203 | Vintage Design | My Remote | 7/25/2023 12:20:00 AM | 7/25/2023 12:45:00 AM | 0 | 0 | 0.42 | 0 | 0 | S. Sharma | CHD-TS1 | Support | Remote | Review the my remote portal, and found the machines VDI164,VDI191,VDI203 running with old version of screenconnect. So reinstalled the latest version 23.5.7.8593. from my remote portal. After that refresh the machine from the portal. It was updated to latest version. Hence closing this ticket.
Under Contract | 7/25/2023 | ScreenConnect Ver. 23.2.9.8466 updated on the following machines - VDI144,VDI169. | Vintage Design | My Remote | 7/25/2023 12:20:00 AM | 7/25/2023 12:35:00 AM | 0 | 0 | 0.25 | 0 | 0 | S. Kumar | CHD-TS1 | Support | Remote | Reviewing on my remote portal, We found that the following machines- VDI144,VDI169 (23.2.9.8466) were using an outdated version of ScreenConnect. Hence, access to the machine. updated to new version 23.5.7.8593 successfully after uninstalling the previous version.
Under Contract | 7/25/2023 | Natalie's Emails | Vintage Design | Office 365 / Gsuite | 7/25/2023 3:30:00 AM | 7/25/2023 3:45:00 AM | 0 | 0 | 0.25 | 0 | 0 | M. Kumar | CHD-TS1 | Support | Remote | Logged into portal and removed the forwarding as per client request.
Under Contract | 7/26/2023 | Need to install Technijian tools on VDI208 | Vintage Design | Project Work | 7/26/2023 4:40:00 PM | 7/26/2023 5:11:00 PM | 0.52 | 0 | 0 | 0 | 0 | N. Ahmad | CHD-TS1 | Support | Remote | Technijian tools has been installed on the VDI208 1. Crowd strike installed on the machine 2. Malwarebytes installed 3.MyRmm installed 4.My Remote installed 5.Chrome installe Windows updates also installed on the machine Task complete
Under Contract | 7/26/2023 | teams not working | Vintage Design | Desktop Work | 7/26/2023 7:15:00 AM | 7/26/2023 8:00:00 AM | 0.75 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Irena's teams was not working. Tested FN keys. tested uninstall/reinstall and updates. tested resources locally. tested owa. When Irena openinging link withing work resource it was opening on the ts. I created a link to local install and instructred to use as workaround.
Under Contract | 7/26/2023 | New hire setups | Vintage Design | Desktop Work | 7/26/2023 8:00:00 AM | 7/26/2023 8:30:00 AM | 0.5 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Joining 4 computer to domain and handing off to India to install tools. Followup with Doug and documentation
Under Contract | 7/26/2023 | Technijian tools Installation on Machines. | Vintage Design | Project Work | 7/26/2023 9:00:00 PM | 7/26/2023 9:49:00 PM | 0 | 0 | 0.82 | 0 | 0 | A. Sharma | CHD-TS1 | Support | Remote | Technijian tools ( Malware Bytes, Crowd strike, My RMM, SNMP Service ) have been installed on VDI204, VDI205 & VDI207 machines.
Under Contract | 7/26/2023 | Screenconnect version 23.5.7.8593 updated on machines VDI083-MB,VDI078,VDI201 | Vintage Design | My Remote | 7/26/2023 12:15:00 AM | 7/26/2023 12:40:00 AM | 0 | 0 | 0.42 | 0 | 0 | S. Sharma | CHD-TS1 | Support | Remote | Review the my remote portal, and found the machines VDI083-MB,VDI078,VDI201 running with old version of screenconnect. So reinstalled the latest version 23.5.7.8593. from my remote portal. After that refresh the machine from the portal. It was updated to latest version. Hence closing this ticket.
Under Contract | 7/26/2023 | New Hire documentation with Doug | Vintage Design | Desktop Work | 7/26/2023 12:00:00 PM | 7/26/2023 2:00:00 PM | 2 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Documenting New Hire setups with Doug and seting up 4 users for Sacramento
Under Contract | 7/26/2023 | Screenconnect Latest version (v23.5.7.8593) update :- VDI188 | Vintage Design | My Remote | 7/26/2023 2:15:00 AM | 7/26/2023 2:30:00 AM | 0 | 0 | 0.25 | 0 | 0 | Y. Kumar | CHD-TS1 | Support | Remote | Checked and found the VDI188 devices are running an outdated version of Screen Connect Select and pushed to update from the portal for the new version after the update to verify the version on the portal has some issues. Restarted the screen connect service from the MyRMM and verified that agents have been updated successfully with the latest version. Hence closing the ticket.
Under Contract | 7/26/2023 | Worked on VM migration task for VTD | Vintage Design | Project Work | 7/26/2023 10:15:00 AM | 7/26/2023 11:30:00 AM | 1.25 | 0 | 0 | 0 | 0 | G. Kumar | CHD-TS1 | Support | Remote | Worked on VM migration task for VTD migrated the VBR/ PS01 and NVO3 in progress and DR01 as well and having some issues and troubleshooter the powered off the Vm's and disabled secure boot and started the migration then powered off the VM in HyperV and powered On the Vm in Host and changed the IP address as well.
Under Contract | 7/27/2023 | New hire setups | Vintage Design | Desktop Work | 7/27/2023 7:00:00 AM | 7/27/2023 8:30:00 AM | 1.5 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Setting up mcdermott finish up., wilder to complete and logging in other two users.
Hourly | 7/27/2023 | New hire setups | Vintage Design | Desktop Work | 7/27/2023 12:30:00 PM | 7/27/2023 2:00:00 PM | 2 | 150 | 0 | 0 | 300 | K. Stickel | IRV-TS1 | Support | Onsite | Onsite in Lakeforest to setup final laptop and box up all 3 to ship to Sacramento. Still waiting on other items to arrive.
Under Contract | 7/28/2023 | Remote apps down | Vintage Design | Desktop Work | 7/28/2023 7:00:00 AM | 7/28/2023 8:00:00 AM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Updated from team and migrations troubleshooting on move IP checked, event view checked, investigation of SSL and IIS. Down for hour decided to trouble hoot afterhours shutdown ESXi Virtual Host and turned on Hyper-V virtual host.
Under Contract | 7/28/2023 | New hire setups | Vintage Design | Desktop Work | 7/28/2023 8:00:00 AM | 7/28/2023 9:00:00 AM | 1 | 0 | 0 | 0 | 0 | K. Stickel | IRV-TS1 | Support | Remote | Setup Megan Marrow and configured a desktop workstation.
Under Contract | 7/28/2023 | NOT SCANNING TO FOLDERS | Vintage Design | User Generated | 7/28/2023 12:00:00 AM | 7/28/2023 12:20:00 AM | 0 | 0 | 0.33 | 0 | 0 | S. Kumar | CHD-TS1 | Support | Remote | User mailed in that Scanning to folder not working. So connect to user machine. He has a N drive(Scans) where he has sale folder where all the scan documents goes by default. However its not syncing. The last sync was on 24/07. So connect to the server and showed him the sales folder and he found the Scan file there. Also discussed with Ajay sir and shared the sales folder. So educate the User that as of now use this new drive to Access your data. Our after-hour team will work and fix this permentaly as we need time to troubleshoot. User Agreed. Computer login Password : VDew7512
Under Contract | 7/28/2023 | RE: CUSTOMER CARE GROUP EMAIL ADDRESS | Vintage Design | User Generated | 7/28/2023 12:30:00 AM | 7/28/2023 1:30:00 AM | 0 | 0 | 1 | 0 | 0 | A. Bhardwaj | CHD-TS1 | Support | Remote | Worked on client email to create a shared mailbox and then updated the user delegation. After that called user and then test that with user and it works fine. After that updated few other user on client request.