Statement of Work

SOW-AFFG-003: IT Compliance & VDI Implementation

Prepared for American Fundstars Financial Group LLC

May 1, 2026

CONFIDENTIAL — For authorized use only

Technijian, Inc.  |  18 Technology Dr., Ste 141, Irvine, CA 92618  |  949.379.8499  |  technijian.com

SOW-AFFG-003 — IT COMPLIANCE & VDI IMPLEMENTATION

SOW Number: SOW-AFFG-003

Effective Date: May 1, 2026

Parent Agreement: MSA-AFFG-2026

Client: American Fundstars Financial Group LLC (“AFFG”)

Source: AFFG IT Compliance Strategy (REF: AFFG-CS-2026-04, April 2026)

Regulatory Scope: SEC Reg S-P (2024 Amendments), FINRA Rule 4370, FINRA Rule 3110, SEC Rule 17a-4

Supersedes: This Agreement supersedes the prior Client Monthly Service Agreement between the Parties (DocuSign Envelope F3CDFC05-B156-8A6F-8020-13A164F4E3F1, effective 3/11/2026). Upon the Effective Date of this Agreement, the monthly charges for workstation services, endpoint security, user services, domain/site/IP services, and shared storage set forth in Schedule A shall REPLACE (not be billed in addition to) the corresponding charges under the prior Monthly Service Agreement. The Virtual Staff Support hours and rates under the prior Monthly Service Agreement (CTO Advisory 3 hrs @ $225, US Tech Support 6 hrs @ $125, India Tech Normal 22 hrs @ $15, India Tech After-Hours 8 hrs @ $30) remain UNCHANGED and carry forward into Schedule A, Part 5 of this Agreement at the same rates and contracted hour levels.

|  | 1. Project Overview |
| --- | --- |

Technijian will deliver a 7-phase implementation that migrates AFFG’s seven (7) in-scope registered agents onto the Technijian Horizon VDI (Virtual Desktop Infrastructure) environment — Technijian’s privately-operated, managed Windows 11 desktop service — locks down access to the Microsoft 365 tenant and the Schwab / Interactive Brokers custodial APIs to VDI egress IPs only, deploys data-loss-prevention controls across Exchange Online, SharePoint, OneDrive, and Teams, and produces the full regulator-ready compliance documentation set required under SEC Regulation S-P (including the 2024 Amendments), FINRA Rule 4370, FINRA Rule 3110, and SEC Rule 17a-4.

Objectives:

Deploy Technijian Horizon VDI for 7 in-scope roles with dedicated Windows 11 personal desktops (one per agent)

Restrict M365 and custodian-API access to VDI egress IPs only

Deploy M365 DLP, OneDrive external-sharing lockdown, and email DLP with custodian TLS enforcement

Stand up Veeam 365 Backup with 7-year immutable retention (SEC 17a-4)

Achieve 100% regulatory compliance posture (up from the current ~15% baseline) per the AFFG IT Compliance Strategy

Produce the complete regulator-ready compliance binder (IRP, breach notification, vendor oversight, BCP disclosure, info disposal, annual sign-off)

Exclusions: Technijian My Archive is NOT included under this SOW. AFFG operates its own email-archiving platform, which will remain authoritative for long-term mail retention. Coordination with that platform is included in Phase 4.

|  | 2. 7-Phase Implementation Scope |
| --- | --- |

Project work is organized into forty-one (41) numbered tickets distributed across seven (7) sequential phases, 128 total estimated hours. Each phase below includes the narrative description and the full ticket summary with estimated hours and assigned POD.

|  | Phase 1 — VDI Foundation (Weeks 1–4) |
| --- | --- |

Establish the Technijian Horizon VDI tenant (Technijian’s privately-operated Virtual Desktop service) that will host the seven (7) in-scope AFFG agents. Phase 1 deliverables include the Technijian Horizon VDI workspace and personal host pool, seven (7) dedicated Windows 11 Enterprise personal-desktop VMs, hardened VDI session policies (no clipboard, no local drives, no USB redirection, watermarking, 15-minute inactivity lock), FSLogix profile containers on the Technijian Production Storage pool, MFA and Entra Conditional Access, hands-on enrollment and training, My Audit UAM+DLP agent integration, and documented VDI egress IPs prepared for Schwab and Interactive Brokers allowlisting. This phase enforces the ‘no client data on personal device’ core design principle that underpins the AFFG compliance strategy.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-001 | Technijian Horizon VDI Tenant Setup | 2 | IRV-TS1 |
| AFFG-003-002 | Deploy 7 Technijian Horizon VDI Personal Desktop Images | 2 | CHD-TS1 |
| AFFG-003-003 | Configure VDI Security Policies | 3 | CHD-TS1 |
| AFFG-003-004 | User Profile Management & FSLogix Setup | 2 | CHD-TS1 |
| AFFG-003-005 | MFA & Entra Conditional Access Configuration | 3 | IRV-TS1 |
| AFFG-003-006 | User Enrollment & VDI Access Training | 3 | CHD-TS1 |
| AFFG-003-007 | My Audit UAM+DLP Integration with VDI | 2 | CHD-TS1 |
| AFFG-003-008 | VDI Network Egress IP Configuration | 2 | IRV-TS1 |
| Phase Subtotal | 8 tickets | 17 hrs |  |

|  | Phase 2 — Access Lockdown (Weeks 3–6) |
| --- | --- |

Lock down identity, network, and device perimeters so that production access to AFFG data can only originate from the Technijian Horizon VDI environment or a Technijian-managed, compliant endpoint. Phase 2 refines Entra Conditional Access to restrict M365 sign-ins to the VDI egress IPs across all 31 users, submits and activates Schwab Advisor Services and Interactive Brokers IP allowlists, blocks legacy authentication protocols, deploys CrowdStrike Falcon EDR and Huntress Managed Detection inside each Horizon VDI desktop with Technijian SOC forwarding, deploys the Technijian SSO/2FA gateway to enforce logged MFA on all custodian bank portals and non-M365 systems (Reg S-P §248.30 2024 amendments; NIST IA-2(1)), enrolls all corporate mobile devices in Microsoft Intune MDM with App Protection policies to containerize M365 data on phones (no additional license cost under E3), and configures managed-endpoint device compliance policies requiring Technijian-managed device + MFA + office-IP for any access to regulated systems.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-009 | Entra Conditional Access – VDI-only M365 Sign-ins | 3 | IRV-TS1 |
| AFFG-003-010 | Schwab IP Allowlist Request Processing | 2 | IRV-TS1 |
| AFFG-003-011 | Interactive Brokers IP Allowlist Setup | 3 | CHD-TS1 |
| AFFG-003-012 | Block Legacy Authentication in Entra ID | 2 | CHD-TS1 |
| AFFG-003-013 | Endpoint Protection Deployment on VDI (CrowdStrike + Huntress) | 4 | CHD-TS1 |
| AFFG-003-014 | SSO/2FA Gateway for Custodian Bank Portals & Non-M365 Systems | 3 | IRV-TS1 |
| AFFG-003-015 | Intune MDM Enrollment & App Protection (MAM) Policies | 3 | CHD-TS1 |
| AFFG-003-016 | Managed Endpoint Device Compliance Policy | 2 | CHD-TS1 |
| Phase Subtotal | 8 tickets | 22 hrs |  |

|  | Phase 3 — Data Protection / DLP (Weeks 5–8) |
| --- | --- |

Deploy Microsoft 365 Data Loss Prevention across Exchange Online, SharePoint, OneDrive, and Teams. Phase 3 defines custom Sensitive Information Types for Schwab and IBKR account-number patterns, locks down OneDrive external sharing, configures email DLP rules with TLS enforcement for custodian domains, and executes end-to-end exfiltration testing with sign-off by AFFG’s registered principal.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-017 | M365 DLP Policies for PII / SSN / Account Numbers | 6 | IRV-TS1 |
| AFFG-003-018 | OneDrive External Sharing Restrictions | 2 | CHD-TS1 |
| AFFG-003-019 | Email DLP Rules Configuration | 4 | IRV-TS1 |
| AFFG-003-020 | Sensitive Information Types (SITs) Setup | 4 | IRV-TS1 |
| AFFG-003-021 | DLP Testing & Validation | 4 | CHD-TS1 |
| Phase Subtotal | 5 tickets | 20 hrs |  |

|  | Phase 4 — V365 Backup (Weeks 7–10) |
| --- | --- |

Stand up Veeam 365 Backup against the AFFG Microsoft 365 tenant — Exchange Online mailboxes, SharePoint sites, OneDrive accounts, and Teams data for all 31 users — with a 7-year immutable retention policy on the Backup Storage tier to satisfy SEC Rule 17a-4. Phase 4 also configures the M365 Compliance Center eDiscovery (Standard) workspace and coordinates with AFFG’s existing email-archive platform so long-term mail retention remains authoritative there.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-022 | Veeam 365 Backup Deployment | 3 | CHD-TS1 |
| AFFG-003-023 | Configure 7-Year Retention + Immutability | 2 | CHD-TS1 |
| AFFG-003-024 | eDiscovery Workspace Setup | 2 | CHD-TS1 |
| AFFG-003-025 | Coordinate with AFFG's Existing Email Archive | 3 | IRV-TS1 |
| Phase Subtotal | 4 tickets | 10 hrs |  |

|  | Phase 5 — Monitoring & Audit (Weeks 9–12) |
| --- | --- |

Bring the supervisory and monitoring surface to full regulator-ready coverage. Phase 5 confirms My Audit UAM+DLP is operational across all 7 Horizon VDI desktops, enables detailed Technijian Horizon VDI session logging with central forwarding, builds insider-threat and anomaly alerting (off-hours sign-ins, impossible travel, mass-deletion, after-hours DLP), delivers the monthly compliance dashboard PDF, documents the FINRA Rule 3110 supervisory audit trail architecture anchored on the dedicated-VM per-agent model, and configures the monthly mobile device audit (enrolled device count vs. headcount, compliance violations, wipe history) folded into the existing Technijian assessment cadence per FINRA 3110(c) and 3120.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-026 | My Audit UAM+DLP Agent Deployment | 3 | CHD-TS1 |
| AFFG-003-027 | Configure VDI Session Logging | 3 | CHD-TS1 |
| AFFG-003-028 | Insider Threat & Anomaly Alerting | 4 | IRV-TS1 |
| AFFG-003-029 | Build Compliance Dashboard | 4 | CHD-TS1 |
| AFFG-003-030 | Supervisory Audit Trail (FINRA 3110) Configuration | 4 | IRV-TS1 |
| AFFG-003-031 | Monthly Mobile Device Audit Configuration | 2 | CHD-TS1 |
| Phase Subtotal | 6 tickets | 20 hrs |  |

|  | Phase 6 — Validation & Testing (Weeks 11–14) |
| --- | --- |

Independently validate the control environment. Phase 6 executes a formal penetration test against the VDI environment (external surface, egress/ingress controls, clipboard/drive/USB bypass attempts, cross-VM isolation, session takeover, privilege escalation), deploys Huntress SAT with financial-services-specific phishing content, baselines the first phishing simulation, and closes with a post-implementation gap assessment against the AFFG IT Compliance Strategy.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-032 | Penetration Test of VDI Environment | 5 | IRV-TS1 |
| AFFG-003-033 | Huntress SAT Deployment (Security Awareness Training) | 3 | CHD-TS1 |
| AFFG-003-034 | Phishing Simulation Setup & Baseline | 3 | CHD-TS1 |
| AFFG-003-035 | Post-Implementation Compliance Gap Assessment | 4 | IRV-TS1 |
| Phase Subtotal | 4 tickets | 15 hrs |  |

|  | Phase 7 — Policy & Compliance Docs (Weeks 13–18) |
| --- | --- |

Produce the regulator-ready documentation set. Phase 7 drafts the Written Incident Response Plan, breach notification procedures and templates (SEC Reg S-P 30-day customer, California Civil Code 1798.82 state AG, FINRA, and custodian), the Service Provider Oversight Policy (incorporating the SEC Reg S-P 72-hour vendor-incident notification clause), the BCP Customer Disclosure (FINRA Rule 4370) plus the Customer Information Disposal Policy, the annual sign-off process, and final packaging of all deliverables into the AFFG regulator-ready compliance binder.

| Ticket ID | Title | Est Hours | Assignee |
| --- | --- | --- | --- |
| AFFG-003-036 | Written Incident Response Plan (IRP) | 5 | IRV-TS1 |
| AFFG-003-037 | Breach Notification Procedures & Templates | 4 | IRV-TS1 |
| AFFG-003-038 | Service Provider Oversight Policy (72-hour clause) | 4 | IRV-TS1 |
| AFFG-003-039 | BCP Customer Disclosure + Info Disposal | 4 | IRV-TS1 |
| AFFG-003-040 | Annual Sign-off & Policy Documentation Process | 5 | CHD-TS1 |
| AFFG-003-041 | Final Compliance Document Packaging & Delivery | 3 | CHD-TS1 |
| Phase Subtotal | 6 tickets | 25 hrs |  |

|  | 3. Regulatory Control Mapping |
| --- | --- |

The table below maps the deliverables of this SOW against the AFFG IT Compliance Strategy regulatory coverage (REF: AFFG-CS-2026-04).

| Regulation | Requirements Covered | Primary Control(s) |
| --- | --- | --- |
| SEC Regulation S-P (2024 Amendments) | 10 of 10 | Technijian Horizon VDI, MyAudit DLP, IP whitelist, SSO/2FA gateway, Intune MDM/MAM, and managed-endpoint device compliance provide the technical safeguards behind the WSP. NIST SP 800-53: AC-3, AC-17, AC-19, IA-2(1), MP-7, SC-7, SC-8. |
| FINRA Rule 4370 | 2 of 2 | BCP customer disclosure, documented business continuity + recovery in Technijian environment |
| FINRA Rule 3110 | 3 of 3 | Per-agent dedicated Horizon VDI VMs, individual accountability, supervisory audit trail with MyAudit UAM+DLP, monthly mobile device audit evidence. NIST SP 800-53: AU-2, AU-12, PS-4. |
| SEC Rule 17a-4 | 3 of 3 | 7-year immutable retention on V365 Backup storage, coordinated archival with AFFG’s existing email archive, eDiscovery workspace |
| NIST SP 800-53 (Rev 5) | Referenced throughout | AC-3, AC-17, AC-19, AU-2, AU-12, CM-8, IA-2(1), MP-5, MP-6, MP-7, SC-7, SC-8. Mapped to each design component in the control-to-citation appendix. |

|  | 4. Deliverables |
| --- | --- |

Live Technijian Horizon VDI environment with 7 dedicated Windows 11 personal desktops

VDI egress IP allowlists approved and active at Schwab Advisor Services and Interactive Brokers

M365 DLP policies deployed across Exchange Online, SharePoint, OneDrive, and Teams, with custom Sensitive Information Types for Schwab and IBKR

Veeam 365 Backup operational with 7-year immutable retention (SEC 17a-4)

My Audit UAM+DLP agents deployed across all 7 Horizon VDI desktops with 1-year retention

Monthly compliance dashboard PDF (MFA rate, DLP events, VDI uptime, backup success, pen-test status, phishing completion)

Penetration test report covering VDI external surface, egress controls, isolation, and privilege escalation

Written Incident Response Plan (IRP)

Breach Notification procedures and templates (SEC Reg S-P 30-day, CA Civ. Code 1798.82, FINRA, custodians)

Service Provider Oversight Policy including the SEC Reg S-P 72-hour vendor incident notification clause

BCP Customer Disclosure (FINRA Rule 4370) + Customer Information Disposal Policy

Annual compliance sign-off process (principal attestation, audit evidence package)

Final regulator-ready compliance binder (encrypted PDF bundle)

Intune MDM/MAM enrollment with App Protection policies on all corporate mobile devices (included in E3)

Monthly mobile device audit evidence (enrolled count, compliance violations, wipe history) per FINRA 3110(c)

SSO/2FA gateway enforcing logged MFA on custodian bank portals and all non-M365 regulated systems

Managed-endpoint device compliance policies (four-factor access boundary: user + MFA + office-IP + managed device)

|  | 5. Pricing and Payment |
| --- | --- |

Labor for this SOW is billed at the hourly (not contracted) rates shown below. Total estimated labor is 128 hours at $12,165.00.

| Role | Rate | Hours | Labor |
| --- | --- | --- | --- |
| US Tech Support (IRV-TS1) | $150/hr (hourly, not contracted) | 61 | $9,150.00 |
| India Tech Support (CHD-TS1) | $45/hr (hourly, not contracted) | 67 | $3,015.00 |
| TOTAL |  | 128 hrs | $12,165.00 |

Payment Schedule:

50% ($6,082.50) due upon SOW execution

25% ($3,041.25) upon Phase 4 completion (V365 Backup operational)

25% ($3,041.25) upon Phase 7 delivery (compliance docs accepted)

|  | 6. Assumptions |
| --- | --- |

AFFG provides administrative credentials to the Microsoft 365 tenant and Entra ID with sufficient privilege to deploy Conditional Access, DLP, and eDiscovery.

AFFG provides timely approvals for the Schwab Advisor Services and Interactive Brokers IP allowlist requests, including any required authorized-signer signatures.

AFFG’s existing M365 tenant is licensed at Microsoft 365 E3 or E5 (or equivalent add-ons) such that Data Loss Prevention and Conditional Access are available.

AFFG’s existing email archive platform meets SEC Rule 17a-4 retention and WORM requirements and can be referenced authoritatively in the Service Provider Oversight documentation.

The 7 in-scope AFFG agents are available for Horizon VDI onboarding and training sessions during Weeks 3–4.

Coordination with third-party vendors (Schwab, Interactive Brokers, AFFG’s email archiver) proceeds on the standard timelines of those vendors; Technijian’s performance dates assume reasonable vendor responsiveness.

Corporate mobile devices (phones with M365 email or OneDrive) are available for Intune MDM enrollment; personal devices may be blocked from M365 apps per the App Protection policy.

|  | 7. Exclusions |
| --- | --- |

Technijian My Archive (AFFG operates its own email-archiving platform, which remains authoritative for long-term mail retention).

Microsoft 365 license costs (AFFG procures M365 licenses directly).

Third-party public cloud consumption costs (all Technijian Horizon VDI resources are provisioned within Technijian’s private cloud and billed via Schedule A, Part 1).

Hardware procurement (AFFG continues to use its existing end-user devices as thin-client access points into VDI; this SOW does not include new workstation purchases).

Any remediation beyond the scope described in the phase narratives; significant remediation work arising from pen-test findings will be scoped under a separate change order.

|  | 8. Ongoing Services |
| --- | --- |

Upon completion of this SOW, AFFG is billed the ongoing recurring charges set forth in Schedule A of MSA-AFFG-2026. The $12,165.00 price of this SOW is a one-time implementation fee and is separate from the Schedule A monthly charges. The tables below compare the current signed monthly contract (DocuSign Envelope F3CDFC05, effective 3/11/2026) against the proposed monthly charges after the SOW is implemented.

Current vs. Proposed Monthly Recurring Charges

| Category | Current Monthly | Proposed Monthly | Change |
| --- | --- | --- | --- |
| Physical Desktops (16 → 9) | $424.00 | $238.50 | –$185.50 |
| Horizon VDI Workstations (7 agents) | — | $2,433.20 | +$2,433.20 |
| All-User Services (31 M365 users) | $263.50 | $441.75 | +$178.25 |
| Domain / Site / IP Services | $112.00 | $162.00 | +$50.00 |
| Shared Storage (4 TB) | — | $500.00 | +$500.00 |
| Virtual Staff Support (unchanged) | $1,995.00 | $1,995.00 | $0.00 |
| TOTAL MONTHLY | $2,794.50 | $5,770.45 | +$2,975.95 |

Proposed Monthly Service Detail

| Service | Code | Qty | Unit Price | Monthly |
| --- | --- | --- | --- | --- |
| HORIZON VDI WORKSTATIONS (7 AGENTS) |  |  |  |  |
| VDI VM (4 vCore / 16 GB / 100 GB) | MYVDI+VM | 7 | $196.00 | $1,372.00 |
| CrowdStrike EDR (on VDI) | AVD | 7 | $8.50 | $59.50 |
| Huntress Managed Detection (on VDI) | AVMH | 7 | $6.00 | $42.00 |
| DNS Filtering (on VDI) | SI | 7 | $6.00 | $42.00 |
| Patch Management (on VDI) | PMW | 7 | $4.00 | $28.00 |
| ScreenConnect (on VDI) | MR | 7 | $2.00 | $14.00 |
| My Audit UAM+DLP / 1-Year | AMDLP1Y | 7 | $108.10 | $756.70 |
| SSO / Multi-Factor | SSO-2FA | 7 | $12.00 | $84.00 |
| Credential Manager | CRM | 7 | $5.00 | $35.00 |
| Subtotal — VDI (7 agents) |  |  |  | $2,433.20 |
| PHYSICAL DESKTOPS (9 REMAINING) |  |  |  |  |
| CrowdStrike EDR (physical) | AVD | 9 | $8.50 | $76.50 |
| Huntress (physical) | AVMH | 9 | $6.00 | $54.00 |
| DNS Filtering (physical) | SI | 9 | $6.00 | $54.00 |
| Patch Management (physical) | PMW | 9 | $4.00 | $36.00 |
| ScreenConnect (physical) | MR | 9 | $2.00 | $18.00 |
| Subtotal — Physical Desktops (9) |  |  |  | $238.50 |
| ALL-USER SERVICES (31 M365 USERS) |  |  |  |  |
| Veeam 365 Backup | V365 | 31 | $4.00 | $124.00 |
| Phishing Training | PHT | 31 | $6.00 | $186.00 |
| Anti-Spam Basic (Inky) | ASB | 31 | $4.25 | $131.75 |
| Subtotal — All-User Services (31) |  |  |  | $441.75 |
| DOMAIN / SITE / IP SERVICES |  |  |  |  |
| DMARC/DKIM Monitoring | DKIM | 1 | $20.00 | $20.00 |
| Site Assessment (Physical Office) | SA | 1 | $50.00 | $50.00 |
| Site Assessment (VDI Environment) | SA | 1 | $50.00 | $50.00 |
| Real-Time Pen Testing | RTPT | 6 IPs | $7.00 | $42.00 |
| Subtotal — Domain / Site / IP |  |  |  | $162.00 |
| SHARED STORAGE |  |  |  |  |
| Production Storage (VDI profiles) | TB-PSTR | 2 TB | $200/TB | $400.00 |
| Backup Storage (V365 / SEC 17a-4) | TB-BSTR | 2 TB | $50/TB | $100.00 |
| Subtotal — Shared Storage |  |  |  | $500.00 |
| VIRTUAL STAFF SUPPORT (UNCHANGED) |  |  |  |  |
| CTO Advisory (Normal Hours) | IRV-AD1 | 3 hrs | $225/hr | $675.00 |
| US Tech Support (Normal Hours) | IRV-TS1 | 6 hrs | $125/hr | $750.00 |
| India Tech Support (Normal Hours) | CHD-TS1 | 22 hrs | $15/hr | $330.00 |
| India Tech Support (After-Hours) | CHD-TS1 | 8 hrs | $30/hr | $240.00 |
| Subtotal — Virtual Staff Support |  | 39 hrs |  | $1,995.00 |
| PROPOSED TOTAL MONTHLY |  |  |  | $5,770.45 |

The following table summarizes the key monthly recurring charges that result from this SOW’s implementation. These charges represent both new services (VDI, My Audit, V365 Backup, storage) and services carried forward from the prior Monthly Service Agreement. The net increase over the prior agreement is +$2,975.95/month, driven primarily by the Technijian Horizon VDI environment, My Audit UAM+DLP endpoint compliance, and Veeam 365 Backup with 7-year immutable retention.

|  | SIGNATURES |
| --- | --- |

TECHNIJIAN, INC.

By: ___________________________________

Name: _________________________________

Title: _________________________________

Date: _________________________________

AMERICAN FUNDSTARS FINANCIAL GROUP LLC

By: ___________________________________

Name: [AUTHORIZED SIGNER]

Title: _________________________________

Date: _________________________________

Technijian, Inc.  |  18 Technology Dr., Ste 141, Irvine, CA 92618  |  949.379.8499  |  technijian.com