Data Center Network Upgrade — Saturday Migration Schedule

Target Date: Saturday, April 18, 2026  |  Start Time: 9:00 AM  |  Estimated Completion: ~6:00 PM

Devices: Cisco C3850 Stack  |  Nexus N3K01  |  Nexus N3K02  |  Meraki MX

On-site: Sai Revanth (US DC)  |  Remote (India): Parveen Biswal, Gurdeep Kumar, Aditya Saraf, Ajay Bhardwaj

Hour-by-Hour Migration Schedule

| Time | Phase | Who | Tasks / Checkpoints |
| --- | --- | --- | --- |
| 8:00–9:00 AM | Pre-Entry Preparation | All (Remote) | - Team call – confirm all participants are online and runbooks are open - Verify console / OOB access to all devices (N3K01, N3K02, C3850) - Confirm QNAP backup job completed overnight - Review rollback procedure one final time |
| 9:00–10:00 AM | DC Entry & Physical Audit | Sai (On-site) | - Tag ALL cables before touching anything - Document current cabling: UCS Fabric → Nexus ports - Verify Nimble HBA cabling: currently all 4 ports on N3K01 (target: 2 on N3K01, 2 on N3K02) - Verify QNAP cabling: currently all 4 ports on N3K02 (target: 2 on N3K01, 2 on N3K02) - Photograph current state for rollback reference — relay photos to India team - Confirm console / serial access is live to all 3 devices before leaving this phase |
| 10:00–11:00 AM | Physical Recabling | Sai (On-site) + India remote guidance | - Move 2 of 4 UCS Fabric ports from N3K01 → N3K02 (balance: 2×N3K01, 2×N3K02) - Move 2 of 4 Nimble ports to N3K02 (balance storage redundancy) - Move 2 of 4 QNAP ports to N3K01 (balance QNAP redundancy) - Verify all link-lights up after each cable move before proceeding - CHECKPOINT: Confirm no ping loss on management VLAN before continuing |
| 11:00 AM–12:00 PM | C3850 Target Config (Demote to Mgmt-Only) | Parveen / Gurdeep (India) + Sai console | - Console in to C3850 stack - Apply Step 1: no ip routing - Apply Step 2: Rebuild Vlan1 → 10.100.1.10 mgmt-only (172.16.9.10 secondary) - Apply Steps 3–8: Retire all legacy routed SVIs (5-6, 12-14, 100-109, 114, 240-245, 253-254) - Apply Step 10: Remove legacy default route via 10.100.1.1 - CHECKPOINT: Ping 10.100.1.10 from management network — must succeed |
| 12:00–1:00 PM | N3K01 Target Config (Full SVI Buildout) | Parveen / Gurdeep (India) + Sai on-site | - Apply Step 1 (N3K01): Remove legacy ACLs after full configuration we will apply new ACL - Apply Step 3: Rebuild Vlan1 → 10.100.1.2, HSRP priority 110, VIP 10.100.1.1 - Apply Steps 4–21: Build SVIs for VLANs 2–255 in batches - Apply Step 8: VLAN49 MX_TRANSIT → 10.100.49.2, HSRP priority 110 - Apply Step 22: Update physical links (Eth1/6, Eth1/25, Eth1/26) + TrueNAS port-channel - Apply Step 23: Remove old static routes; add ip route 0.0.0.0/0 10.100.49.254 - CHECKPOINT: Verify HSRP VIP 10.100.1.1 active on N3K01, management reachable |
| 1:00–1:30 PM | Lunch Break / Buffer | All | - 30-min break — at least one person (India team) monitoring ping to management VIP |
| 1:30–2:30 PM | N3K02 Target Config (Full SVI Buildout) | Parveen / Gurdeep (India) + Sai on-site | - Apply Step 1 (N3K02):Remove legacy ACLs after full configuration we will apply new ACL - Apply Step 2: Rebuild Vlan1 → 10.100.1.3, HSRP priority 90 - Apply Steps 3–21: Build SVIs for VLANs 2–255 in batches - Apply Step 7: VLAN49 MX_TRANSIT → 10.100.49.3, HSRP priority 90 - Apply physical link updates: Eth1/5/1 Meraki VLAN49 trunk, Eth1/8/1 C3850 uplink, Eth1/26 TrueNAS - Remove legacy static routes; apply target routes - CHECKPOINT: Verify HSRP active/standby roles correct across N3K01/N3K02 |
| 2:30–3:00 PM | Meraki / Internet Cutover | Parveen (India) + Sai on-site | - Disconnect internet cable from C3850; connect directly to Nexus uplink (or verify VLAN49 path) - On Meraki: remove legacy VLANs; create VLAN49 as transit VLAN - Update all static routes on Meraki → next-hop via VLAN49 (10.100.49.254) - VERIFY: 1-to-1 NAT rules on firewall still intact (no changes needed) - Test internet connectivity from at least 3 different VLANs - CHECKPOINT: All client VLANs reaching internet through Nexus/Meraki/VLAN49 path |
| 3:00–4:00 PM | Full Verification & Smoke Tests | All | - Ping HSRP VIPs for all critical VLANs (1, 6, 7, 49, 100, 107) - Verify UCS vCenter accessible and all blades/hosts online - Verify Nimble storage accessible from ESXi hosts (datastores mounted) - Verify QNAP backup jobs can be triggered manually - Test CloudBrink portal connectivity (CB_PASSPORTAL, CB_MYRMM, CB_MYREMOTE VLANs 12-14) - Verify VLAN isolation: confirm cross-VLAN blocking per ALL-VLAN-ISOLATION ACL - Verify TrueNAS port-channel on VLANs 6–7 via N3K01 Eth1/26 + port-channel10 |
| 4:00–4:30 PM | IP Schema Review (Ravi Decision Gate) | All | - Present Ravi with go/no-go on 172.x → 10.x IP migration - If YES: Schedule UCS blade IP changes (downtime required for blade VMs) - If NO: Leave 172.x management IPs as-is; defer to future window - Either way: confirm ACL VLAN isolation is working (no inter-VLAN talk) |
| 4:30–5:30 PM | Buffer / Contingency Time | All | - 1-hour buffer for any unexpected issues from above phases - Use for: any failed checkpoints, re-cabling needs, config corrections - If all phases completed ahead of schedule, use for documentation updates |
| 5:30 PM onward | Close-Out / Rollback Decision Point | All | - If all checkpoints PASSED: declare change successful, close maintenance window - If critical failure: initiate rollback (see Rollback Plan below) - Document any deviations from the runbook - Send success/completion email to Ravi Jain |

Rollback Plan

Each phase has a discrete rollback. Reverse steps in the order listed (bottom to top). Parveen leads rollback CLI execution; Sai coordinates on-site physical actions.

| Phase to Rollback | Rollback Action |
| --- | --- |
| Route change | Re-apply legacy static routes on N3K01/N3K02; remove ip route 0.0.0.0/0 10.100.49.254 |
| Meraki cutover | Restore legacy VLANs on Meraki; remove VLAN49; repoint static routes to legacy next-hops |
| C3850 SVI retirement | Apply C3850 Legacy→Target rollback runbook steps in reverse; re-enable ip routing |
| N3K01 SVI buildout | Apply N3K01 Legacy→Target rollback runbook (reverse of forward steps) |
| N3K02 SVI buildout | Apply N3K02 Legacy→Target rollback runbook (reverse of forward steps) |
| Physical recabling | Re-photograph and reverse each cable move one at a time; verify link-lights at each step |

Team Assignments

| Name | Location | Primary Responsibility |
| --- | --- | --- |
| Sai Revanth | On-site (DC) | Physical presence, hands-on cabling, console access, on-site coordination & liaison to Ravi |
| Parveen Biswal | Remote (India) | Config lead – Nexus SVI buildout, Meraki changes, primary CLI executor |
| Gurdeep Kumar | Remote (India) | Config support – assists Parveen, verification steps, parallel monitoring |
| Aditya Saraf | Remote (India) | Documentation, runbook tracking, records all changes for rollback reference |
| Ajay Bhardwaj | Remote (India) — if available | Additional config/verification support as needed |
| Ravi Jain | On-call | Decision gate at 4:00 PM, emergency escalation |

Key Notes

- Zero downtime is NOT achievable — plan for a service window and notify stakeholders in advance.

- Sai is the only physical presence in the DC. All cable work and console access flows through Sai, directed remotely by the India team.

- India team (Parveen, Gurdeep, Aditya) should be in a shared call/screen-share for the entire duration so commands can be reviewed before Sai pastes them.

- The 1-hour buffer (5:00–6:00 PM) is reserved for contingency. Do not start ahead of schedule — use it as cushion.

- IP schema migration (172.x → 10.x on UCS blades) requires a separate window — this Saturday change does NOT include blade IP changes unless Ravi approves at the 4:00 PM gate.

- Console / OOB access MUST be verified before any config changes begin. Do not rely on in-band management during cutover.

- Runbook documents to have open: N3K01_Exact_Delta_Runbook, N3K02_Exact_Delta_Runbook, C3850_Exact_Delta_Runbook.