Statement of Work

Oaktree Law — Server Migration & Cloud Hosting

March 23, 2026

Technijian, Inc.

18 Technology Dr., Ste 141  |  Irvine, CA 92618  |  949.379.8499

# STATEMENT OF WORK

SOW Number: SOW-OKL-001

Effective Date: March 23, 2026

Master Service Agreement: MSA-OKL-2026

This Statement of Work ("SOW") is entered into by and between:

Technijian, Inc. ("Technijian")

18 Technology Drive, Suite 141

Irvine, California 92618

and

Oaktree Law ("Client")

[CLIENT ADDRESS]

[CITY, STATE ZIP]

Primary Contact: Ed Pits

# 1. PROJECT OVERVIEW

## 1.1 Project Title

Physical Server Migration to Technijian Cloud with Cloudbrink ZTNA and OneDrive Migration

## 1.2 Project Description

Oaktree Law currently operates a physical on-premises server that requires migration to a cloud-hosted environment. This SOW covers:

Full migration of the existing physical server to Technijian's private cloud datacenter

Deployment of a Cloudbrink Zero Trust Network Access (ZTNA) virtual appliance for secure user access

Migration of approximately 779 GB of shared folders to Microsoft OneDrive / SharePoint Online

Deployment of security and management agents (CrowdStrike, Huntress, Patch Management, My Remote)

Ongoing managed hosting, security, and support services

## 1.3 Current Environment

| Component | Specification |
| --- | --- |
| Processor | Intel Xeon E3-1220 v5 @ 3.00 GHz (2 processors) |
| Memory | 14.0 GB RAM |
| Local Drive (C:) | 119 GB total / 3.33 GB free |
| Shared Storage (D:) | 779 GB total / 60.7 GB free |
| Internet | 500 / 500 Mbps symmetric |

# 2. SCOPE OF WORK

## 2.1 In Scope

Full discovery and assessment of the existing physical server environment

Provisioning of two (2) virtual machines in the Technijian datacenter

Physical-to-Virtual (P2V) migration of the existing server to VM1

Deployment and configuration of Cloudbrink ZTNA virtual appliance on VM2

Migration of shared folders (~779 GB) to Microsoft OneDrive / SharePoint Online

Installation of security agents: CrowdStrike, Huntress, Patch Management, My Remote

Deployment of Veeam backup for both virtual machines

End-to-end testing, validation, and go-live cutover

30-day post-migration support period

## 2.2 Out of Scope

Desktop/workstation support, upgrades, or reimaging

Email migration or Microsoft 365 tenant configuration

Line-of-business application reconfiguration beyond basic validation

Procurement of Microsoft 365 / OneDrive licenses (Client responsibility)

Physical decommissioning or disposal of the old server hardware

Cloudbrink per-user subscription licensing (billed separately by Cloudbrink)

Network equipment upgrades at Client's office

## 2.3 Assumptions

Client will provide administrative credentials and access to the existing server

Client will ensure all critical data is backed up prior to migration start

Client's 500/500 Mbps internet is sufficient for Cloudbrink performance

Client has or will procure Microsoft 365 licenses with OneDrive/SharePoint storage

Migration work will be performed during off-hours to minimize disruption

# 3. PROJECT PHASES

## Phase 1: Discovery & Assessment

Comprehensive audit of the existing physical server including installed roles, services, applications, shared folder structure, permissions, and network configuration.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| CTO Advisory | Migration strategy, architecture planning, risk assessment | $250/hr | 2 | Week 1 |
| Tech Support (US) | Server audit, inventory, and documentation | $150/hr | 2 | Week 1 |
|  | Phase 1 Total |  | 4 |  |

## Phase 2: Cloud Environment Provisioning

Provision and configure the target environment in Technijian datacenter: two virtual machines, storage, networking, and firewall rules.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| Tech Support (US) | VM provisioning and OS install | $150/hr | 4 | Week 1-2 |
| Tech Support (US) | Network and storage configuration | $150/hr | 2 | Week 1-2 |
| Tech Support (Offshore) | Backup setup (Veeam) | $45/hr | 2 | Week 2 |
|  | Phase 2 Total |  | 8 |  |

## Phase 3: Physical-to-Virtual Server Migration

Migrate the server OS and applications (~119 GB local volume) to VM1 via P2V. Shared folder data (~779 GB) is migrated separately to OneDrive/SharePoint in Phase 4. Includes pre-migration backup, driver remediation, Windows activation, service validation, and network cutover.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| Tech Support (US) | Pre-migration backup verification and snapshot | $150/hr | 2 | Week 2 |
| Tech Support (US) | P2V conversion setup (Disk2VHD / Veeam) | $150/hr | 2 | Week 2-3 |
| Tech Support (Offshore) | Data transfer monitoring (~119 GB OS volume) | $45/hr | 2 | Week 2-3 |
| Tech Support (US) | Driver cleanup, HAL remediation, VM tools install | $150/hr | 2 | Week 3 |
| Tech Support (US) | Windows activation, licensing validation | $150/hr | 1 | Week 3 |
| Tech Support (US) | Server role/service validation (AD, DNS, DHCP, file shares, print) | $150/hr | 3 | Week 3 |
| Tech Support (US) | DNS/IP reconfiguration and network cutover | $150/hr | 2 | Week 3 |
| Tech Support (Offshore) | Performance validation and baseline comparison | $45/hr | 2 | Week 3 |
|  | Phase 3 Total |  | 16 |  |

## Phase 4: Shared Folder Migration to OneDrive / SharePoint

Migrate ~718 GB of shared folder data to SharePoint Online / OneDrive for Business. Includes site architecture design, pre-migration file remediation (long paths, special characters), NTFS-to-SharePoint permission mapping, incremental migration runs, and per-workstation OneDrive sync client setup.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| CTO Advisory | SharePoint site collection architecture and library design | $250/hr | 2 | Week 3 |
| Tech Support (US) | SharePoint Migration Tool setup and configuration | $150/hr | 2 | Week 3 |
| Tech Support (Offshore) | Pre-migration file scan and remediation (long paths, special chars) | $45/hr | 3 | Week 3 |
| Tech Support (US) | Initial bulk migration kickoff (~718 GB) | $150/hr | 2 | Week 3-4 |
| Tech Support (Offshore) | Migration monitoring, failed item resolution, delta sync | $45/hr | 3 | Week 4 |
| Tech Support (US) | NTFS-to-SharePoint permission mapping and validation | $150/hr | 4 | Week 4 |
| Tech Support (Offshore) | OneDrive sync client deployment on user workstations | $45/hr | 2 | Week 4-5 |
| Tech Support (US) | User training session and quick-reference guide | $150/hr | 2 | Week 5 |
| Tech Support (Offshore) | Post-migration validation (file counts, integrity, access) | $45/hr | 2 | Week 5 |
|  | Phase 4 Total |  | 22 |  |

## Phase 5: Cloudbrink ZTNA Deployment

Deploy Cloudbrink ZTNA virtual appliance on VM2. Includes tenant configuration, connector deployment, Microsoft Entra ID integration, application resource definitions, per-user ZTNA policies, split tunneling, and agent deployment to each end-user device.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| CTO Advisory | ZTNA architecture, policy design, application resource planning | $250/hr | 2 | Week 5 |
| Tech Support (US) | Cloudbrink tenant setup and connector deployment on VM2 | $150/hr | 2 | Week 5 |
| Tech Support (US) | Microsoft Entra ID (Azure AD) identity provider integration | $150/hr | 2 | Week 5 |
| Tech Support (US) | Split tunneling, routing, and performance tuning | $150/hr | 1 | Week 5 |
| Tech Support (Offshore) | Cloudbrink agent deployment to end-user devices | $45/hr | 3 | Week 5-6 |
| Tech Support (US) | Multi-location access testing and troubleshooting | $150/hr | 2 | Week 6 |
|  | Phase 5 Total |  | 12 |  |

## Phase 6: Security & Management Agent Deployment

Install and configure all security and management agents on both virtual machines.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| Tech Support (US) | Agent installation and configuration | $150/hr | 2 | Week 6 |
| Tech Support (Offshore) | Validation and reporting verification | $45/hr | 2 | Week 6 |
|  | Phase 6 Total |  | 4 |  |

## Phase 7: Testing, Validation & Go-Live

End-to-end testing of migrated server, OneDrive/SharePoint access, Cloudbrink ZTNA connectivity, and all security agents. Coordinated production cutover during a planned maintenance window.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| CTO Advisory | Go-live coordination, cutover plan review, client sign-off | $250/hr | 2 | Week 6 |
| Tech Support (US) | End-to-end functional testing (server, apps, shares) | $150/hr | 3 | Week 6 |
| Tech Support (US) | Coordinated go-live cutover (DNS, firewall, routing) | $150/hr | 2 | Week 6-7 |
| Tech Support (Offshore) | Cloudbrink and OneDrive access validation with end users | $45/hr | 1 | Week 7 |
| Tech Support (Offshore) | Post-cutover monitoring (first 48 hours) | $45/hr | 2 | Week 7 |
|  | Phase 7 Total |  | 10 |  |

## Phase 8: Post-Migration Support (30 Days)

30-day post-migration support period for issue resolution, performance tuning, and user assistance.

| Role | Description | Rate | Hours | Timeline |
| --- | --- | --- | --- | --- |
| Tech Support (US) | Escalated issue resolution and performance tuning | $150/hr | 2 | Weeks 7-11 |
| Tech Support (Offshore) | Routine support tickets, monitoring, user assistance | $45/hr | 6 | Weeks 7-11 |
|  | Phase 8 Total |  | 8 |  |

# 4. PRICING AND PAYMENT

## 4.1 Rate Card

| Role | Location | Rate |
| --- | --- | --- |
| CTO Advisory | United States | $250.00/hr |
| Tech Support | United States | $150.00/hr |
| Tech Support | Offshore (India) | $45.00/hr |

## 4.2 One-Time Migration Labor

| Phase | Description | CTO ($250) | US Tech ($150) | Offshore ($45) | Total Hrs | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Discovery & Assessment | 2 | 2 | — | 4 | $800.00 |
| Phase 2 | Cloud Environment Provisioning | — | 6 | 2 | 8 | $990.00 |
| Phase 3 | Server Migration (P2V) | — | 12 | 4 | 16 | $1,980.00 |
| Phase 4 | OneDrive / SharePoint Migration | 2 | 10 | 10 | 22 | $2,450.00 |
| Phase 5 | Cloudbrink ZTNA Deployment | 2 | 7 | 3 | 12 | $1,685.00 |
| Phase 6 | Security Agent Deployment | — | 2 | 2 | 4 | $390.00 |
| Phase 7 | Testing & Go-Live | 2 | 5 | 3 | 10 | $1,385.00 |
| Phase 8 | Post-Migration Support | — | 2 | 6 | 8 | $570.00 |
| TOTAL |  | 8 | 46 | 30 | 84 | $10,250.00 |

CTO Advisory: 8 hrs x $250/hr = $2,000  |  Tech Support US: 46 hrs x $150/hr = $6,900  |  Offshore: 30 hrs x $45/hr = $1,350

Pricing Type: Estimate Cost — Actual time billed at the applicable rate. If hours are projected to exceed the estimate by more than 10%, Technijian will notify Client before proceeding.

## 4.2 Ongoing Monthly Services — Technijian Datacenter (Recommended)

Cloud Infrastructure (2 VMs)

| Service | Code | Qty | Unit Price | Monthly |
| --- | --- | --- | --- | --- |
| VM1 — vCores (Primary Server) | CL-VC | 4 | $6.25 | $25.00 |
| VM1 — Memory (GB) | CL-GB | 16 | $0.63 | $10.08 |
| VM1 — Shared Bandwidth | CL-SBW | 1 | $15.00 | $15.00 |
| VM2 — vCores (Cloudbrink) | CL-VC | 2 | $6.25 | $12.50 |
| VM2 — Memory (GB) | CL-GB | 4 | $0.63 | $2.52 |
| VM2 — Shared Bandwidth | CL-SBW | 1 | $15.00 | $15.00 |
| Production Storage | TB-PSTR | 1 TB | $200.00 | $200.00 |
| Backup Storage | TB-BSTR | 1 TB | $50.00 | $50.00 |
| Infrastructure Subtotal |  |  |  | $330.10 |

Microsoft Licensing

| Service | Code | Qty | Unit Price | Monthly |
| --- | --- | --- | --- | --- |
| Windows Server Std — 2-Core Pack | MS-STD | 4 | $5.25 | $21.00 |
| Licensing Subtotal |  |  |  | $21.00 |

Security & Management Agents (2 Servers)

| Service | Code | Qty | Unit Price | Monthly |
| --- | --- | --- | --- | --- |
| CrowdStrike — Server | AVS | 2 | $10.50 | $21.00 |
| Huntress — Server | AVHS | 2 | $6.00 | $12.00 |
| Patch Management | PMW | 2 | $4.00 | $8.00 |
| My Remote | MR | 2 | $2.00 | $4.00 |
| Security Subtotal |  |  |  | $45.00 |

Backup & Recovery

| Service | Code | Qty | Unit Price | Monthly |
| --- | --- | --- | --- | --- |
| Image Backup (Veeam) | IB | 2 | $15.00 | $30.00 |
| Backup Subtotal |  |  |  | $30.00 |

TECHNIJIAN TOTAL MONTHLY:  $426.10

TECHNIJIAN TOTAL ANNUAL:  $5,113.20

## 4.3 Azure Equivalent Monthly Cost (For Comparison)

Equivalent cost to host the same environment in Microsoft Azure (pay-as-you-go, West US 2 region):

| Service | Azure SKU | Monthly |
| --- | --- | --- |
| VM1 — Primary Server | D4s v5 (4 vCPU, 16 GB) Windows | $281.00 |
| VM2 — Cloudbrink Appliance | B2s (2 vCPU, 4 GB) Linux | $31.00 |
| Managed Disk | 1 TB Premium SSD (P30) | $123.00 |
| Azure Backup | Recovery Services Vault (1 TB) | $55.00 |
| Outbound Data Transfer | ~500 GB egress / month | $44.00 |
| Static Public IP | 1 Standard Static IP | $4.00 |
| Windows Server License | Included in VM pricing | $0.00 |
| CrowdStrike — Server | 2 servers | $21.00 |
| Huntress — Server | 2 servers | $12.00 |
| Patch Management | 2 servers | $8.00 |
| My Remote | 2 servers | $4.00 |
| Azure Monitor | Basic monitoring & alerts | $15.00 |
| AZURE TOTAL MONTHLY |  | $598.00 |
| AZURE TOTAL ANNUAL |  | $7,176.00 |

## 4.4 Cost Comparison Summary

|  | Technijian Datacenter | Microsoft Azure | Savings |
| --- | --- | --- | --- |
| Monthly Cost | $426.10 | $598.00 | $171.90 (28.7%) |
| Annual Cost | $5,113.20 | $7,176.00 | $2,062.80 (28.7%) |
| 3-Year Cost | $15,339.60 | $21,528.00 | $6,188.40 (28.7%) |

Technijian Datacenter Advantages:

28.7% lower monthly cost compared to Azure pay-as-you-go pricing

$2,062.80 annual savings on hosting alone

No egress / bandwidth charges — shared bandwidth included

No surprise Azure consumption charges — predictable, fixed monthly billing

Local Technijian support team manages infrastructure end-to-end

Single vendor for hosting, security, backup, and support

Included Veeam backup — enterprise-grade with faster recovery

No Azure expertise required from Client

## 4.5 Payment Schedule

| Milestone | Invoiced | Amount |
| --- | --- | --- |
| Project kickoff (before Phase 1) | Upon SOW execution | $5,125.00 (50%) |
| Go-live completion (after Phase 7) | Upon go-live | $5,125.00 (50%) |
| Monthly managed services | 1st of each month | $426.10/month |
| ONE-TIME PROJECT TOTAL |  | $10,250.00 |

All invoices are due and payable within thirty (30) days of the invoice date.

# 5. CLIENT RESPONSIBILITIES

Client shall:

(a) Provide administrative credentials and physical/remote access to the existing server;

(b) Designate Ed Pits (or alternate) as the authorized point of contact;

(c) Review and approve deliverables within five (5) business days of submission;

(d) Ensure all critical data is backed up prior to migration start;

(e) Inform users of planned service changes, maintenance windows, and downtime;

(f) Procure and maintain Microsoft 365 licenses with adequate OneDrive/SharePoint storage (~779 GB); and

(g) Coordinate with Cloudbrink for per-user ZTNA subscription licensing.

# 6. CHANGE MANAGEMENT

6.01. Any changes to the scope, schedule, or pricing of this SOW must be documented in a written Change Order signed by both Parties.

6.02. If Client requests out-of-scope work, Technijian shall provide a Change Order detailing the additional work, estimated hours, and cost impact.

6.03. Technijian shall not proceed with out-of-scope work without an approved Change Order, except where delay would harm Client's systems.

# 7. ACCEPTANCE

7.01. Upon completion of each phase, Technijian shall notify Client that deliverables are ready for review.

7.02. Client shall review and provide written acceptance or a description of deficiencies within five (5) business days.

7.03. If Client does not respond within the review period, deliverables shall be deemed accepted.

# 8. GOVERNING TERMS

The terms of the Master Service Agreement (MSA-OKL-2026) shall govern this SOW. In the event of a conflict between this SOW and the MSA, the MSA shall prevail unless this SOW expressly states otherwise.

## SIGNATURES

TECHNIJIAN, INC.

By: ___________________________________

Name: _________________________________

Title: _________________________________

Date: _________________________________

OAKTREE LAW

By: ___________________________________

Name: Ed Pits

Title: _________________________________

Date: _________________________________