Executive Summary

Server Migration & Managed Cloud Hosting

Prepared for Oaktree Law

March 2026

CONFIDENTIAL — For authorized use only

Technijian  |  18 Technology Dr., Ste 141, Irvine, CA 92618  |  949.379.8499  |  technijian.com

|  | Overview |
| --- | --- |

Technijian proposes migrating Oaktree Law’s aging physical server to a fully managed cloud environment hosted in Technijian’s private datacenter. The project includes server virtualization, migration of 779 GB of shared data to Microsoft OneDrive/SharePoint, deployment of Cloudbrink Zero Trust Network Access (ZTNA) for secure remote connectivity, and installation of enterprise security agents across all systems.

Upon completion, Oaktree Law will have a modern, secure, and fully managed IT infrastructure with predictable monthly costs, enterprise-grade backup, and 24/7 monitoring — eliminating the risk and maintenance burden of on-premises hardware.

|  | What’s Included |
| --- | --- |

Cloud-Hosted Servers: 2 virtual machines in Technijian’s private datacenter replacing your physical server

Data Migration: 779 GB of shared folders migrated to OneDrive/SharePoint with full permission mapping

Zero Trust Access: Cloudbrink ZTNA for secure access from anywhere — no VPN needed

Enterprise Security: CrowdStrike endpoint protection, Huntress threat hunting, automated patch management

Managed Backup: Veeam image-level backup of both VMs with daily snapshots and rapid recovery

30-Day Post-Migration Support: Dedicated support for issue resolution and user assistance

|  | Project Timeline |
| --- | --- |

| Phase | Description | Timeline |
| --- | --- | --- |
| 1 | Discovery & Assessment | Week 1 |
| 2 | Cloud Environment Provisioning | Weeks 1–2 |
| 3 | Physical-to-Virtual Server Migration | Weeks 2–3 |
| 4 | OneDrive / SharePoint Data Migration | Weeks 3–5 |
| 5 | Cloudbrink ZTNA Deployment | Weeks 5–6 |
| 6 | Security Agent Deployment | Week 6 |
| 7 | Testing, Validation & Go-Live | Weeks 6–7 |
| 8 | Post-Migration Support (30 Days) | Weeks 7–11 |

|  | One-Time Migration Cost |
| --- | --- |

| Role | Rate | Hours | Cost |
| --- | --- | --- | --- |
| CTO Advisory (US) | $250/hr | 8 | $2,000 |
| Tech Support (US) | $150/hr | 46 | $6,900 |
| Tech Support (Offshore) | $45/hr | 30 | $1,350 |
| TOTAL |  | 84 hours | $10,250 |

Payment Schedule: 50% at project kickoff ($5,125)  +  50% at go-live ($5,125)

Pricing Type: Estimate — actual time billed at applicable rate. If hours exceed estimate by >10%, Technijian will notify before proceeding.

|  | Ongoing Monthly Services |
| --- | --- |

| Category | Services Included | Monthly |
| --- | --- | --- |
| Cloud Infrastructure | 2 VMs (vCores, Memory, Shared BW) + 1 TB Prod + 1 TB Backup Storage | $330.10 |
| Microsoft Licensing | Windows Server Std — 4x 2-Core Packs | $21.00 |
| Security & Monitoring | CrowdStrike (2), Huntress (2), Patch Mgmt (2), My Remote (2) | $45.00 |
| Backup & Recovery | Veeam Image Backup (2 VMs) | $30.00 |
| TOTAL MONTHLY |  | $426.10 |
| TOTAL ANNUAL |  | $5,113.20 |

|  | Cost Comparison: Technijian vs. Azure |
| --- | --- |

| Period | Technijian | Azure | Savings |
| --- | --- | --- | --- |
| Monthly | $426.10 | $598.00 | $171.90 (28.7%) |
| Annual | $5,113.20 | $7,176.00 | $2,062.80 (28.7%) |
| 3-Year | $15,339.60 | $21,528.00 | $6,188.40 (28.7%) |

Technijian Datacenter Advantages:

Predictable, fixed monthly billing — no surprise Azure consumption charges

No egress or bandwidth charges — shared bandwidth included

Single vendor for hosting, security, backup, and support

Enterprise-grade Veeam backup with faster recovery than Azure Backup

Local Technijian support team manages infrastructure end-to-end

|  | Total Investment Summary |
| --- | --- |

| Item | Amount |
| --- | --- |
| One-Time Migration (84 hours) | $10,250.00 |
| Monthly Managed Services | $426.10/month |
| Year 1 Total (migration + 12 months hosting) | $15,363.20 |
| Year 2+ Annual Cost (hosting only) | $5,113.20/year |

|  | Agreement Structure |
| --- | --- |

Master Service Agreement (MSA): Governs the overall relationship, payment terms, confidentiality, liability, and dispute resolution for a 12-month initial term with automatic annual renewal.

SOW-001 — Server Migration: Defines the 8-phase migration project scope, deliverables, timeline, and one-time pricing. Governed by the MSA.

Schedule A — Monthly Services: Details the ongoing managed hosting, security, and monitoring services with SLA commitments.

Schedule C — Rate Card: Establishes hourly rates for any additional work or change orders.

|  | Next Steps |
| --- | --- |

1. Review this summary and the attached agreements

2. Confirm client address and any questions with Ed Pits

3. Sign the MSA, Schedule A, Schedule C, and SOW-001

4. Technijian begins Phase 1 Discovery within 5 business days of execution

Technijian, Inc.  |  18 Technology Dr., Ste 141, Irvine, CA 92618  |  949.379.8499  |  technijian.com

CONFIDENTIAL — Prepared exclusively for Oaktree Law